## 28 May 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates
GPDM- 28453 | Mass import of Documents | Waiting for Support | Spoorthy | Ragu | This ticket already been discussed with song ha and it needs to be checked with tech team on who has to do the import, Is it AMS or AD team. And check whether he needs a "Demand" to be created by Song Ha for this | Ragu mentioned to send an email to Ravi asking for the process to handle these kind of requests looping Song Ha
GPDM-28456 | [5 empty] | Discussed during the Prod issues meeting, Ragu recommended deleting the duplicate workflow processes that contain approval details
GPDM- 28466 | [5 empty] | Discussed with Ragu, and he confirmed that we can proceed with manually setting them to ‘Released’ and and mention it on the set State that this was handled within the Change Notice, as suggested by Oliver Ley. We can revisit this if the issue occurs again.

## 26 May 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates
GPDM- 28317 | Document Back to Draft status | Waiting for Support | Venkat | Ragu | Work around tested : For 54 documents - Selected documents in Approved state (approved earlier) from the Dialyzers container. Changed the document state to Draft (So that new iteration wont get created) Updated the state back to Approved using the migadmin user Republished the document and reviewed the output. Verified that the watermark still displayed the original (older) approval timestamp, confirming that the system retains the initial approval date. ----------------------------------- For 11 documents - Latest iteration can be deleted ---------------------------------------- Song Ha agreed to have this applied on 54 docs and the remaining 11 can be fixed by deleting the latest iteration

## 21 May 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates
GPDM-28092 | Documents cannot be renamed anymore, even in version A.1 | Waiting for Support | Shashank | Tech team | Need to know from Ragu if they need a PI on this. | Ragu will check and update on the next steps.
GPDM-28317 | Document back to draft statues | Waiting for Support | Venkata | Tech team | Approved docs(66 of them) were added to Promotion Request, and once the PR was rejected the status on these docs changd back to "Draft". On 11 docs it was on a new iteration and on 54 it was on same iteration. We need to check with tech team today on whether they have some solution to correct the Doc status on the 54 docs.(By removing the Draft and bringing it back to Approved one) | Ragu mentioned that for approved documents, it is not possible to create promotion requests. We need to verify if these are older documents where the transition may not have been updated. For the 54 documents, Ragu suggested testing in QA first. To proceed, we need to update the state back to 'Approved' using the migadmin user to avoid generating a recent approval timestamp, as the logic ignores updates made by migadmin when capturing the approval timestamp watermark. We should update the records in QA and share our observations with Ragu before proceeding with Production.

## 19 May 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments
GPDM-28092 | Documents cannot be renamed anymore, even in version A.1 | Waiting for Support | Shashank |  | Discussed ticket with Song Ha, Need to check with Tech Team if this is a regression issue from previous PRODUCTION ISSUE 468409 and if Verification Implementation Manager role is restricting the Member role functionality.
GPDM-28286 | GBL-SUP-069122, Rev B, Status Issue | Waiting for Support | Spoorthy | Tech team

## 14 May 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments
GPDM-28286 | GBL-SUP-069122, Rev B, Status Issue | In progress | Spoorthy | Ragu |  | Ragu will look into this
REQ0450780/TASK0470393 | Windchill: Quality records "VJR-007-24X" and "TDR 25X-006" are no longer needed and will not be approved. | Pending | Vaibhav | Ragu | User confirmed that we have to delete these 2 objects | Ragu cinfirmed that we can proceed with deletion

## 12 May 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments
GPDM-28179 | Thumbnail creator issue with large assembly | Waiting for support | Nikhil | Ragu | The job for assembly 1000039124, Version A.25 has been published; however, the thumbnail did not generate. According to PTC article CS465291, increasing the Short Timeout value of helper may resolve this issue. We requested Andreas to check in the object into QA so that we can test publishing via the command line in QA instead of Production. Andreas mentioned like, “That’s not possible. The device consists of thousands of parts, and completing this would take several days. Furthermore, it would result in something different from what currently exists in production.” | To raise PTC ticket.If they mention to execute the job in commandline, we may have to do it during the off hours.
GPDM-28236 | The language value is not visible in the general field within the document shells. | Waiting for support | Bhargavi | Ragu | Request: Extend the General section in the document shell so the Language field is visible without scrolling. Justification: Colleagues often miss filling in the Language field because it is not immediately visible, so they don’t realize their mistake. Song Ha’s Opinion: This enhancement is considered low priority. However, she would like to first assess technical feasibility and implementation complexity with the Tech team. One concern is that many existing documents have a Description field with large, multi-row content in the General section. Even if the section is initially expanded to show the Language field, it may still become hidden again when other fields expand and take up additional space. | This section cannot be resized and it is OOTB feature. Options available is to rearrange layout and can place language attribute below 'Description' attribute

## 07 May 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments
GPDM-28179 | Thumbnail creator issue with large assembly | Waiting for support | Nikhil | Ragu | The job for assembly 1000039124, Version A.25 has been published; however, the thumbnail did not generate. According to PTC article CS465291, increasing the Short Timeout value of helper may resolve this issue. Kindly review and confirm whether we can adjust the Short Timeout setting.

## 05 May 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments
GPDM--27660 | CNs attached to end items |  | Sakshi | Ragu | https://dev.azure.com/FreseniusMedicalCare/PDM%20-%20Product%20Data%20Management/_workitems/edit/494240 Is created in ADO

## 28 April 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
GPDM--27660 | CNs attached to end items | Waiting for support | Sakshi | Ragu | User replied that "this is needed for " Project Overpass Fx""Need a way to see what CNs are present in the end items to create new structures and expedite the process. Can we go ahead with the creation of ADO ticket?
GPDM- 28092 | Documents cannot be renamed anymore, even in version A.1 | In Progress | Shashank | Ragu

## 23 April 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
GPDM--27660 | CNs attached to end items | Waiting for support | Sakshi | Ragu | The user has requested a list of all the CNs attached to the END Item. To address this we have created two reports in QA based on assosiation types 'Resulted' and 'Affected by'. These reports have been reviewd by Oliver. | Ragu suggested checking with the user to understand the usage of these reports. Specifically, whether they are intended to be used across multiple containers and by multiple users. If so, the standard process should be followed: a new report specification should be created in ADO and promoted to Production as part of a release. In that case, the report context should be set at the Fresenius (organization) level.
TASK0446000 | hh‑Corp‑Assignment Search |  |  |  |  | If the user is comfortable with the 'Completed by' value as User ID, please obtain their confirmation via email and then seek Ravi’s approval to deploy the change to Production. Once approved, capture these details in the Jira ticket and proceed with implementing the changes in Prod after Ravi’s approval.

## 21 April 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
GPDM-27958 | Document Approval is not possible | Waiting for customer | Vinothkumar | Ragu | User has Document control Manager role and when they route the document for approval, they are getting roll back error
TASK0453478 | Windchill Keyword Search Problem | Work in Progress | Pushpa

## 16 April 2026
Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting | Updates during Meeting
1 | REQ0424127 - TASK0446000 | Some workflows in windchill that are appearing when I run a report but never existed in the file | Pending | Divya | Ravi | According to our observation & understanding, we communicated user that the discrepancy occurs because the Audit Trail and the hh‑Corp‑Assignment Search report pull information from two separate data sets in the database. As a result, it is not feasible to modify the hh‑Corp‑Assignment Search report to show the completing user instead of the assigned owner. But now user is asking if it is possible to add the "completing user" along with "assigned owner" to hh‑Corp‑Assignment Search to correct the daily metric reporting?

## 14 April 2026
Sr. no. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-27682 | Access Reset - Julya Rebellato | Waiting for customer | Nikhil | Tech team

## 07 April 2026
Sr. no. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-27638 | Expand of selection for classification reference 92-06-07-00 | In progress | Nikhil | Ragu | The user has requested that ‘Printable bright paper’ be added to the raw material field for classification reference 92‑06‑07‑0 as soon as possible in order to proceed with creating a new specification. Kindly confirm weather we can proceed with request.
2 | GPDM-26568 | 191117 Design and Manufacturing Revs do not match | Waiting for Support | Sakshi | Tech Team | Awaiting approval on AA 469529
3 | GPDM-27539 GPDM- 27538 GPDM-27518 | There are two consecutive approval entries under Maturity History for DIP and published file is showing migrated date as 'Approved' date. This document is a migrated object. Activity_Issue_Kalypso_admin | Waiting for support | Divya/ Venkata | Ragu/Nishant |  | This is complex change and tech team to look into it.
4 | GPDM-27446 | Reviewers of CA-LIRs Incorrectly Assigned | Waiting for support | Spoorthy

## 31 March 2026
Sr. no. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-27539 GPDM- 27538 GPDM-27518 | There are two consecutive approval entries under Maturity History for DIP and published file is showing migrated date as 'Approved' date. This document is a migrated object. Activity_Issue_Kalypso_admin | Waiting for support | Divya | Ragu/Nishant |  | This is complex change and tech team to look into it.
2 | GPDM-27577 | List of QDOO approvals - The user is looking for list of User Account Records for an audit where the user is the 'Sign As Creator' for the workflow | Waiting for support | Divya | Tech team |  | There is no export option under 'My Tasks'
3 | GPDM-27446 | Reviewers of CA-LIRs Incorrectly Assigned | Waiting for support | Spoorthy | Tech team |  | Ragu to update the comments in the Jira | GPDM-27446 | Reviewers of CA-LIRs Incorrectly Assigned
4 | GPDM-27478 | Restore deleted documents in the GPDM Windchill container | In progress | Sakshi | Tech team | The user requested to restore deleted document in windchill container. We discussed this with Song Ha, and she advised us to cross‑check the request with the technical team. Could you please confirm whether there is any available method or possibility to restore a deleted document in Windchill? | Unfortunately deleted documents cannot be restored. | GPDM-27539 GPDM- 27538 GPDM-27518 | There are two consecutive approval entries under Maturity History for DIP and published file is showing migrated date as 'Approved' date. This document is a migrated object. Activity_Issue_Kalypso_admin
5 | GPDM-26568 | 191117 Design and Manufacturing Revs do not match | Waiting for support | Sakshi | Tech team | As Bren has completed and confirmed his validation on the QA environment, we now need Raghu’s approval to proceed with running the utility on the Production server. | Ravi's approval is required. ADO status to be updated
6 | GPDM-26980 | PDR Tasks for GBL-M-055103 and GBL-M-055104 | Waiting for support | Nikhil | Ragu/Nishant | This ticket was discussed in the recent calls. As per the update, we requested Amy to create the PI for the issue. However, Amy commented on the ticket and asked Ragu/Nishant to verify why the PDR was assigned twice within 30 days, as it should only be sent once per year. | Nishant and Ragu to discuss internally
7 | GPDM-27467 | controlled copies not automatically asked to reconcile | Waiting for support | Gowthami | Ragu | Just to update you, Chetan is reviewing the issue. | AD team is working on this
WCNA | TASK0438339 & TASK0443115 | Generic Request | Work In Progress | Pushpa | Ragu | User is requesting for additional symptom codes to appear and wanted to understand the logic behind how these codes are populated for 'Complaint Summary & Review Workflow' tasks | Gowthami and Divya to connect with Ragu on document update utility

## 26 March 2026
Sr. no. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-26980 | PDR Tasks for GBL-M-055103 and GBL-M-055104 | Waiting for support | Nikhil | Ragu/Nishant | We requested Amy to create the PI. She raised a concern about assigning the PDR twice within a 30‑day period.

## 24 March 2026
| Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-27487 | Explain the difference between business requirements and the QDOK settings for planned periodic review date | In Progress | Divya | Tech Team |  | This is how it was configured in the previous QDOK system as well
2 | GPDM-27253 | Updating of fields in the GMQ EMEA Serbia library in GPDM (QDOK) according to the attached list | Waiting for support | Nikhil | Ragu | The user has requested the addition of new values to the following enumerations: - - Responsible Area - Area of Application They are expecting this change to be completed within 10 business days. However, as discussed during the GPDM Production Issues call, Nishant highlighted that this change would require a detailed impact analysis, as it could lead to regression issues. Due to this dependency, the change cannot be safely implemented within 10 business days. Could you please confirm if we can inform this revised expectation to Amy and the user? | This need to come as a CR and can be implemented only during next release. This cannot be completed in 10 days
3 | GPDM-27289 | 0896351 - change of "required check indicator" needed | Waiting for support | Venkat | Ragu | We are seeking approval from Ragu to update the attribute value using IBAUtility. | Got approval from Ragu to execute the utility

## 17 March 2026
| Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-27253 | Updating of fields in the GMQ EMEA Serbia library in GPDM (QDOK) according to the attached list | Waiting for support | Nikhil | Tech team | The request is to add the following new values to the ‘Responsible Area’ and ‘Area of Application’ enumerations: Microbiology Manufacturing – Extrusion Process EHS Logistics Warehouse General Support The user expects this to be completed within 10 working days. We discussed the ticket with Amy, and she advised: “Please ask the technical team how long it would take to create these new groups.” Kindly review and confirm the estimated effort so that the CR can be created. | Nishant confirmed that this cannot be completed in 10 business days, as it required detailed impact analysis. Nishant informed to confirm this with Ragu
2 | GPDM-27041 | Change state of document | waiting for support | Nikhil | Tech team | Amy manually change the documents from Effective back to Approved. The PDF Reader didn't not update bases on these manual updates. The portal show the correct information on the UI, but the PDF representation is not correct.Can you please correct the Reader Effective should show for VIV-CMD-001898 Rev 4 and VIV-CMD-001919,6 | Published version 4 and version 6 again and it fixed the issue
4 | GPDM-27289 | 0896351 - change of "required check indicator" needed | Waiting for support | Venkat | Tech team | for the article code 0896351 Off-the-shelf Part - 0896351, ETHANOL 96 % purest, tax free, Fresenius, B.1 (EMEA_StWendel) the field “Requiired check indicator” (tab ERP details) needs to be set to “YES” as requested in change. | Nishant confirmed that this can be implemented using IBAUtility. However we need approval from Ragu

## 10 March 2026
| Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-27120 | Notification of overdue activity for a task that has already been completed | Waiting for support | Nikhil | Tech team | The user completed the document review on February 20, 2026, but still received an overdue notification. We previously resolved a similar issue in PDOC under Production Issue 349339 and Change Request 354670. The same issue has now occurred in QDOK. This ticket was discussed in the global support meeting, and they recommended consulting the tech team. Kindly review the issue and confirm whether a PI/CR is required in QDOK. | Nishant/ Siva will discuss internally with Ragu and will create a CR for this issue
2 | GPDM-27231 | Approver list - 2 questions | Waiting for support | Spoorthy | Tech team |  | Nishant/ Siva will discuss internally with Ragu and will create a CR for this issue
3 | GPDM-27258 | 134644613- stuck in Executing state in WfUserWorkQueue for workflow DOP‑0000108667. | resolved | Shashank | Ragu | I discussed this with Siva from the Tech team, and he mentioned he will provide an update tomorrow. Based on his update, we can proceed either to complete the Delete Temp File activity or terminate the workflow. | Siva informed to complete 'Delete temp file' task as the document is in 'Pending Approval' state.If any document is in 'Approved' state, we should not complete this task | Done

## 5 march 2026
| Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-26568 | 191117 Design and Manufacturing Revs do not match | In progress | Sakshi | Ragu | As per discussion with Ragu we have created ADMIN[ ACTIVITY 469529] to run the OOTB utility to fix all duplicate Part to Process Plan links. We tested this OOTB utility in INT2 server. need confirmation to procced on QA server. | Ragu has recommended running the utility in the QA environment and noting a few document/part numbers that exhibit the issue. He suggested requesting Bren to validate these items in QA and to have him update the validation details in Admin Activity 469529.
| GPDM-27141 | [5 empty] | Need to check with user about the urgency of this ticket in order to take an action on the task
| GPDM-27138 | [5 empty] | Create an Admin Activity, apply the fix in the QA environment, update the results in the Admin Activity, and then request approval to proceed with the Prod.
| GPDM-27172 | [5 empty] | Ragu mentioned Amy will create a PI and there is a workaround for now
| TASK0428718 | [5 empty] | Ragu asked to reproduce in Windchill NA QA environment, after reproducing complete the task. If this works, request user to complete task on Prod. Also, Ravi mentioned no plan to fix the logic since the WC NA code is frozen.

## 3 march 2026
| Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-27141 | Issue with the "Pending Approval" state of the document | In progress | Nikhil | Ragu | PI to be created
2 | GPDM-27156 | VER-0000319378, P585_m-RFA for Septum 6965211 with E5945C, Fresenius, B.8 | In progress | Sakshi | Ragu | PI to be created
3 | GPDM-27172 | QDOK Reader Issue with Approved Documents | Waiting for support | Spoorthy | Ragu | Tech Team is looking into it.

## 26 Feb 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | INC3079761 | PTC Windchill C-1484690 not transferring to QTRAK | In Progress | Gowthami | Ragu | Upon closure of tasks, the product investigation task for PTC Windchill C-1484690 should transfer to QTRAK. However, this task is not transferring. Task is identified as C-1484690-IntPIA-1792308.
2 | GPDM-26491 | Training Tool - no access possible | Waiting for Support | Spoorthy | Ragu | Ragu confirmed that Amy has already initiated a conversation with Ravi regarding this. The discussions are currently in progress.
GPDM-27044
| GPDM-26568 |  |  |  |  | Create Admin activity and run the utility to remove invalid links for all parts and then proceed with migration to GPDM
| GPDM-27044 |  |  |  |  | Ragu mentioned that we need to identify all parts where the DHF Section value is set to "Design Outputs" and then run the IBA utility to correct the value to "Design Output".

## 24 Feb 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-26909 | REG-0000281504 - issue in the approved Version F | In progress | Jhansi | Tech team | The system is pulling several QDOK documents into the Reference Documents table on the back‑cover page, even though they are not linked to the main document (PDoc) through the Related Objects tab. This behavior is observed across multiple revisions of REG‑0000281504, not only the one reported by the user. We discussed this ticket in the global support meeting, and the recommendation was to investigate with the Tech Team to understand why this is occurring, as it is not expected system behavior. Please advise whether a PI should be raised

## 17 Feb 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-26491 | Training Tool - no access possible | Waiting for Support | Spoorthy | Ragu |  | Ragu mentioned that he is currently in discussions with Ravi regarding this matter.
2 | GPDM-26825 | Unable to add user in notification list approved field. | In Progress | Spoorthy | Ragu |  | Ragu has confirmed that no notifications should be sent to users who do not have access to the GPDM Windchill application. We need to inform the user’s team to refrain from using the Email Notification option and request them to update their internal process accordingly.

## 10 Feb 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-26751 | Add existing user to the new "Non-Medical Software Products" container. | Waiting for customer | Nikhil |  | The ‘Non-Medical Software Products’ container was created using the same template as ‘Digital Solutions,’ but roles like ‘Business’ and ‘Design’ are missing. Need to investigate the cause of this discrepancy. | The same template, “FMC Product Template” used for the Digital Solutions container is also used for the Non‑Medical Software Products container. However, the roles mentioned were added to the Digital Solutions container after the template was originally applied, so they are not included in the base template. As a result, we will need to manually add the missing required roles to the new container.
2 | GPDM-26787 | Please provide the action to add a new review to design input shells |  | Sakshi | Raghu | Could you please clarify why the Windchill Navigate Enterprise collaboration ADU License does not allow user to 'Create New Review' functionality? Would a Windchill Standard Author License required for the user insted? Could you please confirm whether the information we received from the technical team regarding the new PTC licensing model is incorrect in this case? | Ragu confirmed that members who only need to create documents can be assigned the Windchill Navigate Enterprise Collaboration ADU license. However, members who need to 'Create New Review' must be assigned the Windchill Standard Author license.
3 | GPDM-26819 | Overlapping of header and footer in Windchill |  | Sakshi | Raghu | The PI -239011 has been raised for this issue. The PI is in awaiting business state. | This is not a priority request at the moment, as we are currently awaiting an update from the business team. To help us prioritize appropriately, please provide details on the business impact of this issue.
4 | GPDM-26711 | New regulations available in QDATA | In Progress | Jhansi | Raghu |  | Please inform Amy to connect with Ryan to understand the process. Previously, the regulatory libraries were maintained by Roberto and Ryan. If Amy requires any further clarification, she should reach out to Ragu for additional guidance.
5 | GPDM-26537 | SW-FORM-000499: Last Page and red watermarks missing | waiting for support | Spoorthy | Raghu |  | Once the Qdok legacy system is up, Ragu will verify the user data and advise on the next steps. Doug is currently looking into the status of the Qdok legacy system.
6 | GPDM-26791 | Pending action on suspended document revision | In Progress | Spoorthy | Raghu |  | Ragu confirmed to proceed with terminating the task

## 3 Feb 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-26687 | Summary of Local Implementation Instructions not populated in CA-LIRs | Waiting for Customer | Nikhil |  | Currently, the ‘Summary of Local Implementation Instructions’ attribute value is populated on the task 'Receive and Evaluate Local Implementation Request' for all CA‑LIRs from CA‑PREP‑LIR. The user is requesting that this value also be displayed on the 'Details' tab in all CA‑LIRs, so they can view it directly without opening the 'Receive and Evaluate Local Implementation Request' task. If this request is valid, please confirm whether a CR needs to be created for it. | DIscuss with Amy and request her to create a CR if its a valid request
2 | GPDM-25971 | Previous revision still in release status after change | Waiting for Customer | Shashank |  | Currently, there are parts where linkage between MBOM and EBOM is not correctly established listed in Implementation Task 0048390. | Tech team will check and update
3 | GPDM-26714 | 5008 container is missing Elements | In Progress | Shashank |  | User is missing the elements in 5008 container, user is part of both QDOK & PDOC roles, also has GPDM QDOK CAT2 profile and Standard author license | Harleen to create a PTC case for this intermittent issue. Tech team will analyse this.
4 | GPDM-26537 | SW-FORM-000499: Last Page and red watermarks missing | In progress | Spoorthy |  |  | Ragu will check in QDOK legacy system. We need to bring the server up. Doug has requested infra team to resolve the DB error.
5 | GPDM-26568 | 191117 Design and Manufacturing Revs do not match | In progress | Sakshi | Ragu | Need to check if there are any updates on this ticket. | Ragu asked to check the 1st point mentioned by Blake
| GPDM-26526 | [5 empty] | Request CA to submit the PI

## 29 Jan 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | PRODUCTION ISSUE 239011 | Publisher: Header and Footer overlapping |  |  | Ragu | What is the implementation plan for the PI ? We see another ticket GPDM-26400 regarding the same issue. | Awaitng for business, this PI is not related to GPDM-26400. Harleen is analysing on GPDM-26400
2 | GPDM-26556 | Functionality of Backup-System | Waiting for customer | Nikhil | Ragu | Swapna Marabhoina has shared the document CSAS-OP-00000737 for reference. Please advise whether we can provide the PDF version of this document to the user. | Share the document with user and mention that we do not back up individual documents; we only perform a full system restore in case of a disaster.
3 | GPDM-26606 | Incorrect name on application area | In progress | Nikhil | Ragu | The ticket was discussed with Amy, and we identified the solution for updating the attribute. We need guidance on whether the AMS team should implement the changes directly on the production server, or if the tech team will handle it by creating an admin activity | CR needs to be created
4 | GPDM-26568 | 191117 Design and Manufacturing Revs do not match | In progress | Sakshi | Ragu | Need to check if there are any updates on this ticket.
5 | GPDM-26537 | SW-FORM-000499: Last Page and red watermarks missing | In progress | Spoorthy | Ragu

## 27 Jan 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPMD-18612 | Remove Part Responsible |  | Nitin | Ragu | I got the answer from Michael Ohmart: We need to consider all other types of part. There are approx 20-25k data where we will be running Part Responsible now. Michael reported few a part stil showing Part Responsible values. Upon checking, I found that we ran the report and considered the data which was FMC Part type. Michael reported part for "Off-the-shelf Part". Do we need to consider parts for "Off-the-shelf Part" type as well ? | Proceed for all part types as per Michael Ohmert's request
2 | GPDM-26556 | Functionality of Backup-System | Waiting for customer | Nikhil | Ragu | The user clarified that the request is not audit‑related. It is from a periodic document review, and they are asking for the specific standard operating document that outlines the backup process so they can use it as a reference. | Ragu will add a comment on the ticket Summary: We do not back up individual documents; we only perform a full system restore in case of a disaster.
3 | GPDM-26634 | Editing field "Revision history" | In progress | Nikhil | tech team | Song Ha has requested to check with tech team on whether the Revision History being carried over when copying a document is expected system behavior or a potential bug. | Request Song Ha to create CR
4 | GPDM-26568 | 191117 Design and Manufacturing Revs do not match | In progress | Sakshi | Raghu | This part was migrated from WC NA to WC GPDM. The user mentioned that part 191117 was in D revision, but in GPDM, the Design View shows revision E as released, even though no changes have been made. We discussed this ticket with Blake and verified that, in SAP, the part version is E. We also found a previous ticket (GPDM-24395) with the same issue. In that case, the Tech team resolved the issue by running a utility, which updated the D revision in released and created a new revision (E) in the In Work state. We need to check with the Tech team which utility was used and whether they can help apply the same solution to this ticket. | Ragu will review the steps and update us on the next steps.
5 | GPDM-26537 | SW-FORM-000499: Last Page and red watermarks missing | In progress | Spoorthy | Raghu | The user has provided justification for why they cannot put someone else as the document owner. We need to check this with the tech team | Create a user ID, assign the Owner role, publish the document, then delete the user from Windchill. After that, verify how the published document appears, even after republishing in lower envorinment.
6 | ADMIN ACTIVITY 459959 | GPDM NODE1 - Restart One of the Method Server Instance (MethodServer.737892) | New | Nitin | Ravi | Request approval for Admin Activity | Ravi approved, restarted MS on node 1

## 22 Jan 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-26222 | POs Completed Periodic Review but PR Workflow Got Triggered Again | Waiting for customer | Nikhil | Ragu |  | Inform Bonnie to ignore the tasks that were generated from those documents. This is the expected behavior and is functioning as per the system design. If she needs any further clarification, request her to reach out to Amy.
2 | GPDM-26548 | Unable to Edit User Accounts | In Progress | Spoorthy | Ragu |  | Since issue is not reproducible, need to analyse the issue next time. We can close this for now
3 | GPDM-26567 | Tabs are missing from Part view | Waiting for customer | Gowthami | Ragu |  | Tech team has deployed a fix recently, Siva will look into this

## 20 Jan 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | TASK0399237 | GTO support request for Windchill | Pending | Pushpa | Ragu | Jira ticket creation to implement this change first in QA then proceed with Prod | Jira is created https://fresenius.atlassian.net/browse/WCENHANCE-198
2 | GPDM-26504 | QDOK Windchill - New Part & Multiple Parts not showing when creating terms and roles | In progress | Nikhil | Doug |  | Since user is part of Library Manager role, provide Windchill Product Engineering License
| General Ask | Rishikesh has requested to cancel (fail) the executing job for the migrated parts. He mentioned that Ragu indicated the AMS team is aware of a method to handle cancelling (failing) executing jobs. Kindly let us know what is the mentod to cancel (fail) executing the job.

## 15 Jan 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-26293 | DCR PO is mistakenly assigned to Reviewer of LIR tasks | In progress | Jhansi | Ragu | This is an enhancement request. Amy would like to know whether a new ADO ticket should be created or if ticket 19332 should be updated. | Needs to create a new CR for the issue.
2 | GPDM-25595 | QDOK Windchill - wrong group assigned to CA-LIR tasks | In progress | Nikhil | Ragu | Amy seeks clarification: should this be created in ADO, and do we need to meet with the business? Please advise | Tech team is looking into the issue

## 13 Jan 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-14874 | Searching for parts in BOM does not work. | Pending | Nitin | Ragu | This issue was expected to go away with Windchill 13 upgrade, but it still persists. Ragu was in talks with PTC for a fix. | The tech team will deploy a fix, and once it is in production, we should guide users to iterate or revise the part so the changes are reflected.
2 | GPDM-11746 |  | Pending | Nitin | Ragu | CHANGE REQUEST 338971 was planned to implement along with R8.1. Are we considering it for upcoming Release ? | Inform user that this will be prioritized during the next release planning cycle, tentatively for 8.2
3 | GPDM-26328 | DOP-0000112037 revision history missing in Rev.C |  | Shashank | Ragu | Revision History attribute is not present in Prod server and editable using check-out and edit action in INT2 server. | Update Revision History attribute using IBA utility
4 | GPDM-26394 | User is not able to create New Review | In progress | Sakshi | Ragu | Julia Kugler is part of windchill product engineering License and Windchill navigate Enterprise collaboration ADU license. The Product engineering group she is having because of Architecture Author, approver role. This group combination is not allowing her to create New Review. | Provide Windchill Standard Author License to user since user have Windchill Product Engineering License
5 | GPDM-26367 | "Save As" function for Service Part Kit missing | In progress | Prasanthi | Ragu | Save As fuctionality for service part kit was not enabled when user had correct license group added, after adding user to Windchill Standard Author License functionality got enabled user confirmed. | Provide Windchill Standard Author License to user since user have Windchill Product Engineering License
6 | GPDM-26285 | Management of Replacements | Waiting for customer | Nikhil | Ragu | Can we assign licenses on QA/Int2 server for training purpose? User was requesting licenses on these servers because these two servers are connected to their interface systems and they migrated "real" data. | Inform the user that QA will be refreshed from Production, so the same access will be available in QA. If the user requires any specific test account, ask them to verify the corresponding test user with the required roles in the test user sheet

## 08 Jan 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-26198 | Unable to create new DCC under QDOK-DCR-007432 | Waiting for support | Spoorthy | Ragu | The user is encountering an error while trying to create a DCC under QDOK‑DCR‑007432 | Nishant will look into this
2 | GPDM-26292 | New Site and LMR Group Creation Request | Waiting for support | Spoorthy | Ragu | Amy has agreed to create a new group, so we need to inform the tech team about this. Additionally, we should check the business impact to determine whether the existing groups can be deleted | Tech team confirmed this should be addressed as part of a change request for both creation and deletion, as it involves updating QDOKGroup Mapping properties. Request Amy to proceed with creating a CR for this change.
3 | GPDM-26254 |  |  | Venkata Kotra |  | This is Urgent ask. Amy is looking for an update. | Ragu confirmed that he has already discussed with the user (Ryan Kovatch) and is awaiting Ryan’s confirmation
4 | License File | Gayathri was referring some excel file relating to License mapping
5 | GPDM-26285 | Management of Replacements | Waiting for customer | Nikhil

## 06 Jan 2026
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | PRODUCTION ISSUE 307435 | Faulty hyperlinks leading to old QDOK instead of GPDM |  |  | Ragu | User is requesting for the fix | Tech team is already in discussion with user and CA
2 | DEVELOPMENT ACTIVITY 248787 | Create utility to remove MPMPartToProcessPlanLink |  |  | Ragu/Nishant | Utility seems to be deployed in Prod but DA is still opened. Had chat with Nishant and he will check/reconfirm with Ragu | consider this and close the development activity on mpm link deletion utility. https://qservice.intra.fmeone.com/projects/GPDM/queues/custom/140/GPDM-17065
3 | GPDM-26254 | Cant Set Release Target on CA for Approved document and Title Change | Waiting for Support | Venkat Kotra |  |  | Tech team is working on this
4 | GPDM-26222 | POs Completed Periodic Review but PR Workflow Got Triggered Again | Waiting for customer | Nikhil |  |  | Rishikesh will look inot the issue
5 | GPDM-26526 | Approved document cutting off page numbers | In progress | Prasanthi

## 23 Dec 2025
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-26205 | URGENT: REQUEST FOR ADDING APPROVER CHANGE MINOR: CN-0060071, B | Resolved | Venkat |  | Whenever User is set up the particicpant in Complete Implementation Task of CN‑0060071, task is not generating for the requested user. | Ragu to check and confirm the functionality
2 | GPDM-26172 | Completion of CN-0021045 | In Progress | Venkat |  | The user has completed all Implementation and Closure tasks in sequential order. The ‘Sync On Closure Complete’ task was executed in workflow CN‑0021045, but the workflow is not transitioning to the Completed state. Two tasks (0022115 and 0022119) were cancelled in implementation plan, yet the workflow is still running and has not terminated. | Gaurav to analyse further

## 18 Dec 2025
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-25996 | Request for Approval- R&D (No training required because of limitation to viewer and ad hoc approver role) | Waiting for Support | Bhargavi |  | two users have requested Viewer and Ad‑hoc Approver roles in the PD‑Thermosafe container. However, this container does not exist in the system. Upon reviewing PI Issues, we identified a related request, Change Request 92530, which indicates that the product PD‑Thermosafe container was renamed to Nxstage Products and is marked as implemented. (Not having confirmation about the iteration path pointing to the backlog) At the same time, we also came across Production Issue 85088, which appears to contradict the above change request. As discussed with CA's, they are not sure of what exactly was changed around this container in 2022 but there is another container - [Accessories PD machine] whose description says 'contains product data for Thermosafe' | Convey to user that PD‑Thermosafe container is not a valid one, and request if they want the access to Accessories PD machine or NxStage Products.
GPDM-26170

## 16 Dec 2025
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | CHANGE REQUEST 338971 | Implement dynamic template sizing to ensure that header, footer and watermark of PDF representation are displayed properly |  | Nitin | Ragu | This was planned along with Release 8.1 | Inform user that this will be prioritized during the next release planning cycle, tentatively for 8.2
2 | PRODUCTION ISSUE 307435 | Faulty hyperlinks leading to old QDOK instead of GPDM |  | Nitin | Ragu | User is requesting an update | Alyssa will add a comment on PI
3 | GPDM-25788 | Wrong attachment in review protocol | Waiting for support | Bhargavi |  | Last meeting Update: Ragu will discuss with Song Ha and inform that is an OOTB behavior Song Ha Mentioned on CA Chat : No update available, Ragu has not reached out to me yet. Please update to Song Ha | Ragu has added a comment

## 11 Dec 2025
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-25788 | Wrong attachment in review protocol | Waiting for support | Bhargavi |  | Song Ha advised moving the associated document review to the target container. The move action is currently not visible in the system. As mentioned in the previous call, I attempted to connect with the user to confirm whether moved or requested earlier to move the document review. - The user was not available at the time | Ragu will discuss with Song Ha and inform that is an OOTB behavior
| GPDM-25875 | [5 empty] | check with user, if they tried to create using Create Multiple Activities action?
| GPDM-25913 | [5 empty] | Request Song Ha to raise a PI if this is not an expected behavior

## 9 Dec 2025
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-19998 | Display Issue |  |  |  | PTC Case: C17656821 What is the update on PTC case ? | Nitin to check with Kesavan on the ticket history. May be, this is already fixed.
2 | GPDM-25787 | Design Verification Document VER-0000335244 Job stuck in executing state | Waiting for support | Venkata subramanyam |  | We spoke to scott and we checked logs, No findings so far
3 | GPDM-25968 | Windchill GPDM Application Monitoring | Waiting for support | Venkata subramanyam |  | Queue problems Notification Queues -DPNR workflows have servere workflow entries had bad workflow expression we have to force complete the activities, | Subbu to investigate it in detail and get back with findings
4 | GPDM-25788 | Wrong attachment in review protocol | Waiting for support | Bhargavi |  | need to move document review to target container but move action wasn't there and ineligiable objects while moving from advance search option. | This is new or was happening earlier as well
5 | GPDM-25960 | Interface GPDM/SAM.WARE not working | In Progress | Prasanthi |  | Hypercare - Integration Issue reported post GPDM R8.1 GoLive. Juergen/Michael are on it already. PTC case is opened. Can we escalated the case ? | Tech Team is already aware of the issue
6 | GPDM-24163 | Test report shows message "Wet signed" | Waiting for Customer | Nitin Jain |  | Watermark Date is not reflected correctly. | Siva/Ragu will have a look into it
7 | GPDM-24801 | SW-SOP-000159 Rev. 2: Revision history wrong, Wrong numbering of Periodic Review |  |  |  | Incorrect Values. AMy requested to escalate to Tech Team as 'Periodic Document Review Revision History table' is showing incorrect details | Siva/Ragu will have a look into it
8 | GPDM-24973 | [5 empty] | Gowthami will check user's access
9 | GPDM-25875
10 | GPDM-25843

## 2 Dec 2025
S.No. | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | GPDM-25739 | CN is not changing status | Waiting for support | Venkat |  | The CN was terminated by the user, but the state initially changed to Cancelled and is currently showing as Planning. | PRODUCTION ISSUE 443528 is created and will be deployed a spart of 8.1 release
2 | GPDM-25595 | QDOK Windchill - wrong group assigned to CA-LIR tasks | In progress | Nikhil |  |  | Discuss with Amy and confirm to user
3 | GPDM-25794 | change of QDOK_WND_Doc_Controls Group in CAT1 WND Library | In progress | Jhansi |  |  | Reg GPDM-25302, rename QDOK_WND_QA_Approvers_VS.SCC; remove '.' and replace with '_' and inform back to user & add comments as well GPDM-25794. QDOK_WND_Doc_Controls_VS.SCC - create a new group with '_' and not with '.'

## 27 Nov 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
GPDM-24801

## 25 Nov 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 |  | GPDM-25678 | Deliverables do not go to status approved | In progress | Prasanthi |  |  | Try on QA, if changing Format name is working then implement it on PROD
2 |  | GPDM-25597 | Picker for Document Owner attribute when "Edit Multiple Objects" | Waiting for support | Nikhil |  |  | Request CA to submit a new change request for the tech team to work on
3 |  | GPDM-25671 | Modification of user roles "Test Manager" | In progress | Nikhil |  |  | Ragu confirmed to create the user group
4 |  | GPDM-25672 | Modification of user roles "Software Architect" | Waiting for customer | Shashank |  |  | Ragu confirmed to create the user group
5 |  | GPDM-25696 | Transfer document PMA-0000348045 to a different container ""Water & Concentrate Supply" | In progress | Venkat |  |  | If adding to the Viewer role resolves the issue, Ragu suggested adding the AMS support person to the Viewer role temporarily, performing the required action, and then removing from the Viewer role once completed.
|  | GPDM-25446 | role to download whole documentation & create Enhancement request |  | Prasanthi |  |  | Ragu asked to discuss this during the Global Support meeting and update the Blue Space link that creation of an enhancement request cannot be done with a Viewer role. It requires a Contributor license. Usually, with a Viewer role, creation of new objects is not permitted.

## 13 Nov 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 2025-12-11 | GPDM-25522 | Resulting Objects Cancelled in DCC | Waiting for support | Subbu | Tech team |  | Request CA to raise the new change request
2 | 13/11/2025 | GPDM-25523 | PDR Task Not Sent to Document Owner | In Progress | Jhansi | Tech team |  | Tech team asked to republish and mention the user that is an expected functionality. If they needs a change a new CR should be submitted
3 | 13/11/2025 | GPDM-25517 | Task cannot be complted due to rework in promotion approval |  | Venkat |  |  | Tech team mentioned to verify the workflow and check if there are any errors on the 14 resulting objects that did not move to the Pending Approval state and remained in the In Work state. Workaround fix can be to set the state of those objects to Pending Approval and ask the user to complete the task as Rework. Based on the logic, all resulting objects should be moved back to their previous life cycle state.

## 06 Nov 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 2025-06-11 | GPDM-25178 | SMD-WI-000790 Rev 3: 3 different effective dates | Waiting for support | Nikhil | Tech team |  | A PI PRODUCTION ISSUE 413006 has already been created for timezone discrepancy, and the fix will be included as part of the 8.1 release. Regarding historical signatures issue, check with Song Ha or Amy
2 | 2025-06-11 | GPDM-25413 | Windchill GPDM Application Monitoring | Resolved | Nikhil | Tech team

## 30 Oct 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 30-10-2025 | GPDM-25293 | Update/create subscriber groups in discussion as well as in subscription | In progress | Nikhil | tech team | clarification on creating CR for new group creation | Tech team requested more details on where this new group is intended to be used, specifically which containers will use it and whether it is meant to be applied across all containers. Nikhil to get the details from user. Tech team will analyze the impact of creating these groups at the configuration level.
2 | 30-10-2025 | GPDM-25315 | Update subscriber groups in discussion as well as in subscription | In progress | Nikhil | tech team | clarification on creating CR for new group creation | Tech team requested more details on where this new group is intended to be used, specifically which containers will use it and whether it is meant to be applied across all containers. Nikhil to get the details from user. Tech team will analyze the impact of creating these groups at the configuration level.
3 | 30-10-2025 | GPDM-25234 | The recently accessed feature does not give the name of change objects, please consider adding the short description after the change object number. | In progress | Shashank | tech team | Enhancement request: User is requesting to add short description after change object number in recently accessed drop down menu.We checked OOTB it's not possible require customization hence require Devops CR | Need to request CA to raise a CR
4 | 30-10-2025 | GPDM-25000 | Content 2021/2022 | Waiting for Support | Shashank | tech team | User requested for object deletion in Windchill | Ragu mentioned that there is an existing utility to delete related object links. He suggested reviewing the available utilities for link removal, and once the link is removed, the objects can be deleted from Advanced Search. The link should be removed across all iterations.

## 28 Oct 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 28/10/2025 | GPDM-24949 | Supplier can not be opned | waiting for customer | Shahabaz | Tech Team | License issue | Teah team mentioned to create the PI, need to inform Michael Ohmert

## 22 Oct 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
GPDM-25048
|  | GPDM-25158 | GPDM WindchillGPDM-25158 Document is in Pending approval state altough Terminate Task was done. | Waiting for Support | Shahabaz
|  | GPDM-18612 | Remove Part Responsible | Waiting for Customer | Akriti

## 21 Oct 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 |  | GPDM-25158 | GPDM WindchillGPDM-25158 Document is in Pending approval state altough Terminate Task was done. | Waiting for Support | Shahabaz
2 |  | GPDM-18612 | Remove Part Responsible | Waiting for Customer | Akriti
3 |  | GPDM-25126 | mBOM creation issue for F50046906 | In Progress | Bhargavi

## 17 Oct 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | Performance Issue, Node 2, CPU Usages ctossed 90% but no major blockage, some 10-12 active context from 4 hours but not utilizing much CPU
2 | Workflow related issue, User approved but status is still not updated - https://plm.wc.gpdm-euc1.fmcglobal.net/Windchill/app/#ptc1/tcomp/infoPage?oid=VR%3Awt.doc.WTDocument%3A1100489379&u8=1
3 | 2025-10-17 | GPDM-25028, GPDM-25017, GPDM-25141 | Windchill system is too slow. | Waiting for customer | Prasanthi/Bhargavi
GPDM-25109
https://plm.wc.gpdm-euc1.fmcglobal.net/Windchill/app/#ptc1/tcomp/infoPage?oid=VR%3Awt.doc.WTDocument%3A1100489379&u8=1

## 16 Oct 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 2025-10-15 | GPDM-24882 | DNPR Workflow Process is not working correctly | Resolved (workaround) | Venkata Kotra | Tech team | Workflow need to be fixed for specific Task3Completed-Task4SetAttributes | PI-427475
2 | 2025-10-15 | GPDM-25061 | GPDM Application Monitoring | Resolved (Queues ?) | Venkata Kotra | Tech team | Who is responsible to monitor Queue Management & handle severe/failed entries | AMS Team is responsible. AD Team is going through old entries and deleting as appropriate
3 | 2025-10-16 | GPDM-25028 | Technical Issue(GPDM performance is very slow) | Waiting for support | Prasanthi
4 |  | GPDM-24641 | OU Admin acknowledges Periodic Review for GBL-SOP-000180

## 14 Oct 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 2025-10-09 | GPDM-24940 | HN-QR-GEN-00076935_PDF is not displayed completely | In Progress | Nikhil | Tech team
2 | 2025-10-14 | GPDM-25057 | Wrong role being displayed in approval table | In Progress | Venkat | Need to discuss with tech team.

## 9 OCT 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 2025-10-09 | GPDM-24951 | New attributes for OTF-Parts | waiting for customer | Prasanthi | Tech team
2 | 2025-10-09 | GPDM-24940 | HN-QR-GEN-00076935_PDF is not displayed completely | In Progress | Nikhil | Tech team

## 7 Oct 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 2025-07-10 | GPDM-24951 | Re-publish_VERY URGENT | In progress | Nikhil | WINCOM/Tech team

## 2 Oct 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 2025-10-02 | GPDM-24627 | document represented incorrectly | In progress | Jhansi

## 29 sep 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 29/09/2025 | INC2777587 | Change Notice/ Change Activity is editable by Originator during Approval process | In progress | Venkata Kotra | Tech team
2 | 29/09/2025 | GPDM-24558 | Incorrect effective date | waithing for customer | Jhansi | Tech team

## 25 sep 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 25/09/2025 | GPDM-24538 | Rendering process for documents in GPDM after upload takes a lot of time | In progress | Shahabaz | Tech team | performance problem
2 | 25/09/2025 | GPDM-24641 | OU Admin acknowledges Periodic Review for GBL-SOP-000180 | Waiting for support | Jhansi | Tech Team | User is requesting to route the task to this group QDOK_GBL_Local_Admins. The group QDOK_GBL_Local_Admins is not included in Global documentation library | William will check and get back to us
3 | 25/09/2025 | GPDM-18612 | Remove Part Responsible | Waiting for Customer | Akriti | Tech Team | Reporter confirmed to go ahead but we need help with the utility | Need to check with Michael for the list of objects
4 | 25/09/2025 | GPDM-24558 | Incorrect effective date | Waiting for Customer | Jhansi | Tech team

## 22 Sep 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 19/09/2025 | GPDM-24630 | Chad Voty Unable to Approve | In Progress | Shahabaz | Tech Team | workflow task credential fields are grey-out
2 | 22/09/2025 | GPDM-24684 | empty / missing Development Project View for all projects. | Waiting for support | Shahabaz | Tech Team | role access | Resolved
3 | 22/09/2025 | GPDM-24617 | QDOK-DCC-008766 has been set to Cancelled but workflow is not terminated. | Waiting for support | Nikhil | Tech Team | Workflow termination
4 | 22/09/2025 | GPDM-24673 | The user Markus Spengler can not see reference documents. Example see attachment. The second picture shows the same document with the view of another user. | In Progress | Nikhil | Tech Team | For troubleshooting the issue

## 23 sep 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 18-09-2025 | GPDM-24615 | Did not receive email notifications about obsolete CQMS documents | In Progress | Nikhil | Tech Team | After checking logs for email notification issue, couldn't found any related information. | Nishanth to check further
2 | 22/09/2025 | GPDM-24673 | The user Markus Spengler can not see reference documents. Example see attachment. The second picture shows the same document with the view of another user. | In Progress | Nikhil | Tech Team | For troubleshooting the issue | William will check and get back to us
3 | 22/09/2025 | GPDM-24617 | QDOK-DCC-008766 has been set to Cancelled but workflow is not terminated. | Waiting for support | Nikhil | Tech Team | Workflow termination | PI to be raised by user
4 | 23/09/2025 | GPDM-24681 | Periodic Review of SW-FORM-000166 Rev. 1 sent to wrong Person | Waiting for support | Jhansi | Tech Team | I can't modify the Members table because it will remove Matthias from the PDF Published document as the Owner. | William will check and get back to us
5 | 23/09/2025 | GPDM-24641 | OU Admin acknowledges Periodic Review for GBL-SOP-000180 | Waiting for support | Jhansi | Tech Team | User is requesting to route the task to this group QDOK_GBL_Local_Admins. The group QDOK_GBL_Local_Admins is not included in Global documentation library | William will check and get back to us
6 | 23/09/2025 | GPDM-24622 | EOL, EOS and State of multiple parts needs to be updated | Waiting for support | Shahabaz | Tech team | Bulk data need to update | need to update sheet as per logic
7 | 23/09/2025 | GPDM-24630 | Chad Voty Unable to Approve | In Progress | Shahabaz | Tech team | workflow task credential fields are grey-out | Need to add user in memeber role

## 18 Sep 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 18-09-2025 | GPDM-24312 | Issue with Document State | Waiting for Support | Gowroju Jhansi | Tech team | document is currently in an incorrect state
2 | 18-09-2025 | GPDM-24590 | VIV-QR-GEN-00001786, Verzeichnis zur Datenverarbeitung, Fresenius, A.4 | Waiting for Customer | Gowthami Konduri | Tech team | reset the document
3 | 18-09-2025 | GPDM-24615 | Did not receive email notifications about obsolete CQMS documents | In progress | Nikhil Bhiste | Tech team | groups assigned to the list were not notified.
2 | 17-09-2025 | GPDM-24622 | EOL, EOS and State of multiple parts needs to be updated | In progress | Shahabaz | Tech team | Bulk data need to update | Need to check with CA if we can do with the help of advanced seach things
5 | 18/09/2025 | GPDM-24538 | Rendering process for documents in GPDM after upload takes a lot of time | In progress | Shahabaz | Tech team | performance problem | Need to monitor for a week and can be closed later considering the feedback

## 16 Sep 2025
S.No. | Date Added in Sheet | Ticket # | Short Description | Status | Assigned To | To Be discussed with | Action Item/Comments | Updates during Meeting
1 | 16/09/2025 | GPDM-24597 | "Terminate" did not terminate the Document Approval Workflow | Waiting for Support | Shahabaz | Tech Team | Notification robot stuck | date:16/09/2025 technical team will be going to do investigation
2 | 2025-09-16 | GPDM-24395 | Wrong Revision of 180023 on GPDM | Waiting For Customer | Venkat | Tech Team | Need Approval from Ravi/Jeffery | Tech Team will investigate and update.
3 | 16/09/2025 | GPDM-24387 | Windchill GPDM (AMD Product Quality) | Resolved | Nikhil | Tech Team | Information needs to be passed for creating group on QA Env. | We can create the group on QA Env.
4 | 2025-09-16 | GPDM-24602 | Terminate CN task still open for CNs in status "completed" | In Progress | Bhargavi | Tech Team | Updating the LC template will solve the issue suggested by Christian Vogelei
5 |  | GPDM-24312 | Issue with Document State |  | Jhansi | Tech Team